## T-Shirt
Stage 1: Masterfile
Task Number | Task Name | Description | T-Shirt Size | Est. Hours | T-Shirt Size | Estimated Hours Range (example)
1.1 | Creating Masterfile |  | L | 10 | XS | 1 – 2 hours
1.1.1 | Correct naming and hierarchy files, layers |  | S | 2 | S | 2 – 4 hours
1.1.2 | Adjust correct resolution and scale |  | M | 4 | M | 4 – 8 hours
1.2 | Exporting assets from Masterfile |  | S | 2 | L | 8 – 16 hours
1.3 | Structure assets in folders |  | XS | 1 | XL | 16 – 32 hours
|  | Overall Estimation Time: |  | 19
Stage 2: Reskinning assets (UI, reels, symbols, bg, etc..)
Task Number | Task Name | Description | T-Shirt Size | Est. Hours
2.1 | Replace assets in works folder |  | S | 2
2.1.1 | Adjust correct resolution |  | S | 3
2.2 | Creating new assets |  | L | 12
2.2.1 | Adjust by Masterfile (resolution, color, filters, etc..) |  | M | 6
2.2.2 | Creating new animation |  | L | 8
2.3.1 | Correcting scale, naming, hierarchy |  | M | 4
2.3.2 | Animation, mask, weigh corrections |  | M | 4
2.3.3 | Export assets (.JSON, ,spine files) | .JSON, .spine | S | 2
|  | Overall Estimation Time: |  | 41
Stage 3: Fonts reskin
Task Number | Task Name | Description | T-Shirt Size | Est. Hours
3.1.1 | Creating bitmap font sprite |  | L | 8
3.1.2 | Exporting sprite |  | XS | 1
3.1.3 | Import to Shoebox (or similar tool) |  | XS | 1
3.1.4 | Creating bitmap font and .xml |  | S | 2
3.3.1 | Renaming .ttf font |  | S | 2
|  | Overall Estimation Time: |  | 14

## Three point Estimation
Three-Point Estimation | [6 empty] | Example:
[6 empty] | Reskinning symbols and reels | Hours | Notes
• Optimistic – the minimum possible time or cost. | [5 empty] | Optimistic: | 6 | Will be no issues with .spine files and source files (animations, naming, etc..)
• Pessimistic – the maximum possible time or cost. | [5 empty] | Pessimistic: | 10 | May occur some problems with layots, spine files, export, resolution. Need scale fixes
• Most Likely – a realistic estimate that is most to be accurate. | [5 empty] | Most likely: | 8 | May be minor fixes and predictable adjustments
• Expected Case = (O + 4 × ML + P) / 6.
| Task Name | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Expected Est. (E) hours
| Creating Masterfile | 8 | 10 | 14 | 10.3333
| Correct naming and hierarchy | 1 | 2 | 3 | 2
| Adjust resolution and scale | 3 | 4 | 6 | 4.1667
| Exporting assets from Masterfile | 1 | 2 | 4 | 2.1667
| Structure assets in folders | 0.5 | 1 | 2 | 1.0833
| TOTAL (Stage 1) |  |  |  | 19.75
| Task Name | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Expected Est. (E) hours
| Replace assets in works folder | 1 | 2 | 4 | 2.1667
| Adjust resolution | 2 | 3 | 5 | 3.1667
| Creating new assets | 10 | 12 | 16 | 12.3333
| Adjust by Masterfile | 4 | 6 | 9 | 6.1667
| Creating new animation | 6 | 8 | 12 | 8.3333
| Correcting scale, naming, hierarchy | 3 | 4 | 6 | 4.1667
| Animation, mask, weight corrections | 3 | 4 | 6 | 4.1667
| Export assets (.JSON, .spine) | 1 | 2 | 3 | 2
| TOTAL (Stage 2) |  |  |  | 42.5
| Task Name | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Expected Est. (E) hours
| Creating bitmap font sprite | 6 | 8 | 12 | 8.3333
| Exporting sprite | 0.5 | 1 | 2 | 1.0833
| Import to Shoebox | 0.5 | 1 | 2 | 1.0833
| Creating bitmap font and .xml | 1.5 | 2 | 3 | 2.0833
| Renaming .ttf font | 3 | 4 | 6 | 4.1667
| TOTAL (Stage 3) |  |  |  | 16.75

## Parametric Estimation
Parametric Estimation
Task | Time | for example, 1 asset takes 5 minutes to export (includes naming, format check, organizing)
Exporting assets from Masterfile | - | and there are 24 assets in total
Time per asset | 5 min
Total assets | 24
Total time: 5 × 24 | 120 min = 2 hours

## Planning Poker
Expert Judgement: Planning Poker
Planning Poker is a gamified group estimation technique adapted from the Delphi method.
It helps teams reach a consensus when estimating tasks and user stories, making the process more interactive and engaging.
All experts gather in one room.
Each participant is given a set of cards with numbers from the Fibonacci sequence (e.g., 1, 2, 3, 5, 8, 13, etc.).
Example
Task: Creating bitmap font | Time | Comments
Dev1 | 5 hours | I've done similar fonts before; it usually takes for me 4-5 hours.
Dev2 | 8 hours | There's can be issues with custom format + need scaling and styling adjustments
Dev3 | 3 hours | I've done this many times - just a sprite and a Shoebox
Final agreed estimate: 6 hours, medium risk, includes possible issues solving